Minutes for KRC Meeting held on

24/08/2026

# Attendance

- Kasonde Makangila (Mummy)

- Gibstar Makangila

- Daniel Nyimbili

- Betty-Ryan Makangila

- Duke Makangila

- Sharon Nyimbili

- James Makangila

- Dillon Nyimbili

- Davison Muzumara

- Alichimfya Makangila

- Musonda Kaputo

- Caleb Makangila

# Agenda

- Division of roles

General Administrator

Crop Administrator

Equipment manager

Water supply manager

Operations manager

Human Resource Manager

Meeting Coordinator

Piggery Lead

Poultry Lead

- Strategy development for current phase at Chifwema

Water supply and management

Operations - Weekly and Daily planning

Labeling of beds   KRC Meeting schedule

# Division of Roles

Job Descriptions are as follows:

- General Administrator - Responsible for overall coordination of farm trips - budget coordination, overseeing all farm departments.

- Crop Administrator - Responsible for creating, reviewing and sharing of crop growth calendars, schedules and expectations, including monitoring of crop growth and guidance for the team on crop requirements at various growth stages.

- Equipment manager - Responsible for monitoring and recording quantities and state of all equipment, ensuring good care and storage and coordinating purchasing, maintenance and replacement of all farm equipment.

- Water supply manager - Responsible for coordinating water usage and storage, irrigation system installation and maintenance and training of the whole team on appropriate usage and management of water facilities.

- Operations manager - Responsible for weekly and daily planning of target activities. Monitoring progress and improving daily output; i.e. coordinating all daily farm activities.

- Human Resource Manager - Responsible for coordinating all staff(KRC officers and farm employees), team building, role assigning, facilitating training and conflict resolution. Responsible for reinforcing KRC vision, team motivation and attending to individual human resource concerns.

- Meeting Coordinator - Responsible for scheduling and announcement of meetings, writing and sharing of minutes and coordinating weekly KRC meetings.

- Piggery Lead - Responsible for leading in the planning, designing and consolidation of a comprehensive piggery farming blueprint for near future implementation, including budgeting, research, mapping, projections, best practice etc.

- Poultry Lead - Responsible for leading in the planning, designing and consolidation of a comprehensive poultry farming blueprint for near future implementation, including budgeting, research, mapping, projections, best practice etc.

Allocations made in the meeting were as follows:

- General Administrator - Dillon Nyimbili

- Crop Administrator - Alichimfya Makangila

- Equipment manager - Musonda Kaputo

- Water supply manager - Dillon Nyimbili

- Operations manager - Davison Muzumara

- Human Resource Manager - To be determined

- Meeting Coordinator - Betty-Ryan Makangila

- Piggery Lead - To be determined

- Poultry Lead - To be determined

# Strategy Development for Current Phase at Chifwema

## 1. Water Supply and Management

- Both tanks to be filled using the genset every morning starting at 06:00. One worker to be assigned early morning shift to achieve this.

- Back up drums to be filled for storage once the tanks are full.

- Subsequent tank filling for the day to be done using solar power.

- All beds to be watered atleast once a day.

- Drums and watering cans to be purchased to improve watering efficiency.

- Follow ups to be made on installation of drip irrigation and rain hose systems

- Consideration of a way to boost water pressure to facilitate use of multiple taps at once.

## 2. Operations - Weekly and Daily Planning

- Target activities must be set for the following week during each weekly meeting.

- Weekly targets must be posted on the KRC platform for easy access for all.

- Where possible, weekly targets must be allocated to specific days of the said week.

- Watering of all beds to be a fixed target everyday.

- Reviews for the previous week must be shared at each meeting and incomplete tasks pushed forward to the following week.

- A day's work at the farm is considered done once all achievable targets for that day have been met.

- If work for the day is fully achieved before 12:00, consideration must be made about whether to go ahead and prepare lunch or not.

- Every officer going to the farm on a particular day must be seated in the car by 08:00, car leaves by 08:05.

## 3. Labelling of Beds

- All beds must be labelled with labels showing the name of the crop and the date it was planted.

- Labelling to be done for all existing beds and to be done for new beds as they get created.

- Labelling will be done by Davison Muzumara.

- For existing beds where exact planting dates are not available, estimations are permissible.

- Crop Administrator(Alichimfya Makangila) must keep track of all planting dates to correctly track and advise on crop development and requirements.

## 4. Meeting Schedule

- Weekly meetings will be taking place every Thursday at 21:30 at the dining table.

- Duration of the meeting should be up to a maximum of 1 hour per meeting.

- Meeting agendas will always include weekly reviews for the past week and weekly planning for the following week.

- Meetings should facilitate adjustments and improvements of current strategies and systems to track progress and ensure maximum output.

- All are expected to attend weekly meetings.

- Minutes for all meetings will be shared on the KRC platform by the meeting coordinator (Betty-Ryan Makangila).